## Sprint Retrospective
Sprint Retrospective
What went well | What went poorly | What ideas do you have | How should we take action
This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints.
Successfully built core inventory features like FIFO batch tracking, stock deduction, and cancelled-order stock restoration. | FIFO logic was complex and required careful handling to avoid stock mismatch or incorrect profit calculation. | Add more test cases for stock movement, cancelled orders, low-stock alerts, and batch-level pricing. | Create a testing checklist and run it before every major update or deployment.
Dashboard features improved the system by showing revenue, profit, orders, sales trends, and inventory distribution visually. | Some analytics may become slow or harder to read if the database has a large amount of sales and inventory data. | Add filters for date range, category, product, and user role to make dashboard insights more useful. | Optimize dashboard queries and add simple filter controls in the UI.
Role-based access control works well for Admin, Manager, and Staff, helping keep sensitive features protected. | Managing permissions across many routes can become confusing and may cause accidental access issues. | Create a clear permission matrix for all modules like inventory, sales, invoices, users, backups, and reports. | Review all routes and match them against the permission matrix.
Professional invoices, email invoice delivery, and quick print functionality make the sales workflow more complete. | Invoice generation is restricted to completed orders, so users may need clearer feedback when an invoice cannot be created. | Show helpful messages explaining why invoice actions are disabled or unavailable. | Add UI validation messages and status labels near invoice buttons.
Auto-bootstrapping database setup and backup features make the project easier to install and safer to maintain. | Setup may still be difficult for new users because MySQL, .env, and local configuration must be correct. | Add a setup troubleshooting section and sample screenshots for database configuration. | Update the README with common errors, required environment variables, and setup verification steps.